## General Aspects
Procurement Plan |  | Credit No 5005-0 XK | Project ID P112526
Project Name: Kosovo Agriculture and Rural Development Project - Additional Financing
I. General
Agreed date of procurement Plan
Original: | 2017-03-17
Revised: | 2018-03-13
Date of General Procurement Notice: Published on UNDB online on June 26, 2012
II. Goods and Works
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:
| Procurement Method | Procurement Method Threshold (USD) | Prior Review threshold (USD)
1 | ICB (Goods) | ≥ 1,000,000 | ≥ 2,000,000
2 | NCB (Goods) Packages | < 1,000,000 | None
3 | ICB (Works) Packages | ≥ 5,000,000 | ≥ 10,000,000
4 | NCB (Works) Packages | < 5,000,000 | None
5 | Shopping (Goods and Works) | ≤ 100,000 in accordance with 3.5 of the Procurement Guidelines | None
6 | Direct Contracting* | In accordance with paragraph 3.7 of the Procurement Guidelines | Refer to prior review thresholds above for Goods and Works Note: When certain goods are available only from a particular supplier or in cases where compatibility with existing equipment so requirew, these goods may be procured following the Direct contracting method with prior approval from the Bank.
7 | Commercial Practice | In accordance with paragraph 3.13 of the Guidelines up to Euro 1,500,000 million for goods and works | Refer to prior review thresholds above for Goods and Works Note: For rural development sub-projects, of which 50% of agreed costs are reimbursed by the rural development grants.
* all Contracts subject to justification
2. Proposed Procedures for Commercial Practices (CP) (as per paragraph 3.13 of the Guidelines and for community Participation in Procurement (CPP (as per Paragraph 3.19 of the Guidleines: Procurement of goods and works for the rural development sub-projects financed by the rural development grants may be carried out by the farmers in accordance with paragraphs 3.13 and 3.19 of the Procurement Guidelines. Investments eligible for grants may include: improvement of milk collection systems, fruit and vegetable storage and drying facilities, animal waste storage and treatment, support for establishment of small businesses for agro/eco-tourism, etc.
3. Manuals: the client has prepared a draft Project Operations Manual which has a section of Procurement Arrangements to be followed under the project and will develop the Rural Development Grant Procedures for the Rural Grants as well as for the Horticulture Development Grants.
Detailed original procurement contracts for goods, consulting services are enclosed in the next excel spread sheet
III. Selection of Consultants
1. Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
| Selection Method | Procurement method threshold (USD) | Prior Review Thresholds (USD)
1. | Competitive Methods (Firms) QCBS | ≥ 300,000 | ≥ 1,000,000
2 | FBS | In accordance with paragraph 3.5 of the Consultants Guidelines | ≥ 1,000,000
3 | Competitive Methods (Firms) CQ | < 300,000 In accordance with paragraph 3.7 of the Consultant's Guidelines | None
4 | LCS | In accordance with paragraph 3.6 of the Consultants Guidelines | ≥ 1,000,000
5. | Individual Consultants (IC) | In accordance with Section V of the Consultants Guidelines | > 300,000
6. | Single Source (Firms and Individuals)* | In accordance with paragraph 3.8.3.11 of the Consultants Guidelines | Refer to above prior review thresholds for Firms and Individuals
7. | ToRs for Consulting Contracts |  | All
* all Contracts subject to justification
2. Short list comprising entirely of national consultant: Short list of consultants for services, estimated to cost less thant Euro 75,000 equivalent per contract,
may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultants Guidelines.
IV. Rural Grants
The Rural Grant total is EUR 8.80 Million, out of which IDA finances 50%. There will be four calls for proposals. Grants will be administered over two years.
V. Horticulture Development Grants
The Horticulture Development Grant total is EUR 3.00 Million, out of which IDA finances 65%. There will be two calls for proposals. Grants will be administered over two years.
V. Ex-Post review:

## PP
Project Procurement Plan
Project Name: Agriculture and Rural Development, Kosovo - Additional Financing
|  |  | Project ID Number: P112526 |  |  |  |  | Credit No: IDA60170 | [6 empty] | Closing date: | 2021-06-30
|  | Original: | 2016-11-28
|  | Update date: | 2018-03-13
Procurement category | # | Contract # | Description of works | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's review (Prior/Post) | Estimated cost, USD | Source of finance MDTF | Source of finance IDA | Actual contract value equivalent in USD | Draft Bidding Docs and SPN | Bank's NO objection to bidding docs/Specs | Invitation for bids |  | Bid opening | Bid evaluation report |  |  | Bank's no objection to Contract award | Contract Number | Contract signing date | Contract completion date | Winning bidder name&Country |  | Winning bidder name&Country | Remarks | Amount reduced from previous estimates |  | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Total
(Works) | 1 |  |  | Planned |  | W | [22 empty] | #REF! |  | #REF! |  |  |  | #REF!
|  |  |  | Revised | [23 empty] | BB to follow up | #REF! |  |  | 150000 | 350000 | #REF! | #REF!
Actual
| 2 |  |  | Planned |  | W | [22 empty] | #REF! |  | #REF! |  |  |  | #REF!
|  |  |  | Revised | [23 empty] | BB to follow up | #REF! |  |  | 150000 | 350000 | #REF! | #REF!
Actual
| 3 |  |  | Planned |  | W | [22 empty] | #REF! |  | #REF! |  |  |  | #REF!
|  |  |  | Revised |  | W | [21 empty] | BB to follow up | #REF! |  |  | 150000 | 350000 | #REF! | #REF!
Actual
|  |  | Sub Total (Works) | [6 empty] | 0 | 0 | [17 empty] | #REF! |  | #REF! | 450000 | 1050000 | #REF! | #REF!
Procurement category | # | Contract # | Description of goods | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's review (Prior/Post) | Estimated cost of the Project, EUR | Source of finance MDTF | Source of finance IDA | Estimated cost for actual Contract, EUR | Bid Documents and SPN sent to the Bank | Bank's NO objection to Bid Documents | Issue date of the Bid Document/Invitation for Bids | Deadline for Bid submission | Bid opening | Bid evaluation report date or sent to the Bank | Bank's NO to the Bid Evaluation Report | Draft Contract sent to the Bank | Bank's no objection to Contract award | Contract Number | Contract signing date | Contract completion date | Winning bidder name&Country | Comment | Status | Remarks | Amount reduced from previous estimates |  | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Total
(Goods) | 1 | KARP-G-10 | Procurement of equipment for KIA Labs (Contract 1) | Planned | 2 | G | NCB | Post | 250000 |  |  | 250000 | 2018-04-03 | 2018-04-10 | 2018-04-13 | 2018-05-15 | 2018-05-16 | 2018-05-22 | 2018-05-29 | 2018-05-31 | 2018-06-02 |  | 2018-06-05 | 2018-08-07 |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
|  |  |  | Revised | [8 empty] | 2018-09-10 | 2018-09-17 | 2018-09-19 | 2018-10-22 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-07 | 2018-11-12 |  | 2018-11-14 | 2019-01-14
Actual
| 1 | KARP-G-10.1 | Procurement of equipment for KIA Labs (Contract 2) | Planned | 2 | G | NCB | Post | 250000 |  |  | 250000 | 2019-10-02 | 2019-10-09 | 2019-10-12 | 2019-11-13 | 2019-11-14 | 2019-11-20 | 2019-11-27 | 2019-11-30 | 2019-12-04 |  | 2019-12-05 | 2020-02-05 |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
Revised
Actual
| 2 | KARP-G-11 | Equipment for administrative staff for the MA and PA (Purchase of IT Equipment) | Planned | 2 | G | SH | Post | 40000 |  |  | 40000 | 2018-02-01 | 2018-02-08 | 2018-02-12 | 2018-02-26 | 2018-02-27 | 2018-03-02 | 2018-03-09 | 2018-03-12 | 2018-03-14 |  | 2018-03-15 | 2018-04-30 |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
|  |  |  | Revised | [8 empty] | 2019-02-04 | 2019-02-11 | 2019-02-14 | 2019-02-28 | 2019-02-28 | 2019-03-05 | 2019-03-12 | 2019-03-15 | 2019-03-18 |  | 2019-03-20 | 2018-05-02
Actual
| 2 | KARP-G-11 (i) | Equipment for administrative staff for the MA and PA (Purchase of IT Equipment) | Planned | 2 | G | SH | Post | 40000 |  |  | 40000 | 2020-05-04 | 2020-05-11 | 2020-05-13 | 2020-05-27 | 2020-05-28 | 2020-06-01 | 2020-06-08 | 2020-06-10 | 2020-06-12 |  | 2020-06-15 | 2020-08-03 |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
Revised
Actual
| 2 | KARP-G-11.1 | Equipment for administrative staff for the MA and PA (Purchase of Office Furniture) | Planned | 2 | G | SH | Post | 40000 |  |  | 40000 | 2018-02-01 | 2018-02-08 | 2018-02-12 | 2018-02-26 | 2018-02-27 | 2018-03-02 | 2018-03-09 | 2018-03-12 | 2018-03-14 |  | 2018-03-15 | 2018-04-30 |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
|  |  |  | Revised | [8 empty] | 2019-02-04 | 2019-02-11 | 2019-02-14 | 2019-02-28 | 2019-02-28 | 2019-03-05 | 2019-03-12 | 2019-03-15 | 2019-03-18 |  | 2019-03-20 | 2018-05-02
Actual
| 2 | KARP-G-11.1(i) | Equipment for administrative staff for the MA and PA (Purchase of Office Furniture) | Planned | 2 | G | SH | Post | 40000 |  |  | 40000 | 2020-05-04 | 2020-05-11 | 2020-05-13 | 2020-05-27 | 2020-05-28 | 2020-06-01 | 2020-06-08 | 2020-06-10 | 2020-06-12 |  | 2018-03-15 | 2018-04-30 |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
Revised
Actual
| 3 | KARP-G-12 | Office Equipment for PIU | Planned | 3 | G | SH | Post | 52600 |  |  | 52600 | 2018-03-05 | 2018-03-12 | 2018-03-14 | 2018-03-28 | 2018-03-29 | 2018-04-02 | 2018-04-09 | 2018-04-11 | 2018-04-13 |  | 2018-04-16 | 2018-06-04
|  |  |  | Revised | [8 empty] | 2018-12-03 | 2018-12-10 | 2018-12-12 | 2018-12-27 | 2018-12-27 | 2019-01-08 | 2019-01-15 | 2019-01-18 | 2019-01-22 |  | 2019-01-25 | 2019-03-11
Actual
| 4 | KARP-G-13 | Equipment for advisory staff of the MAFRD and Municipalities | Planned | 1 | G | SH | Post | 50000 |  |  | 50000 | 2018-05-07 | 2018-05-14 | 2018-05-16 | 2018-05-30 | 2018-06-01 | 2018-06-05 | 2018-06-12 | 2018-06-14 | 2018-06-18 |  | 2018-06-20 | 2018-08-03
|  |  |  | Revised | [8 empty] | 2018-12-03 | 2018-12-10 | 2018-12-12 | 2018-12-27 | 2018-12-27 | 2019-01-08 | 2019-01-15 | 2019-01-18 | 2019-01-22 |  | 2019-01-25 | 2019-03-11
Actual
|  |  | Sub Total (Goods) | [5 empty] | 762600 | [19 empty] | #REF! |  | #REF! | 0 | 0 | 0 | #REF!
Disbursement Estimates
Procurement category |  | Contract # | Description of Assignment | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's Review (Prior/ Post) | Initial estimated cost, EUR | Source of finance MDTF | Source of finance IDA | Estimated cost for actual Contract, EUR | TOR and ReOI sent to the bank | Bank's no objection to TOR and ReOI | ReOI Published | Deadline for Submission of ReOI | Shortlist and ReOIs Evaluation Report sent to the Bank | Bank's no objection to the Shortlist and ReOIs Evaluation Report | RFP sent to the Bank | Bank's No objection to RFP | Issue date of the RFP | Proposal Submission Deadline | Evaluation Report sent to the Bank | Bank's NO objection to Evaluation report | Bank's No objection to Contract Award | Contract Signing date | Contract Completion | Consultant's Name | Remarks | Amount reduced from previous estimates |  | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Consultant's name | Comment | Status
Component 1 - Transferring Knowledge to the Rural Sector
(Consultant Services) | 1 | KARP-CS-1 (iv) | Training of Potential Applicants for applying to grant programs | Planned | 1 | CS | QBS | Post | 240000 |  |  | 240000 | 2017-10-02 | 2017-10-09 | 2017-10-11 | 2017-10-25 | 2017-10-31 | 2017-11-07 | 2017-10-31 | 2017-11-07 | 2017-11-09 | 2017-12-11 | 2017-12-15 | 2017-12-22 | 2017-12-27 | 2018-01-05 | 2021
|  |  |  | Revised | [8 empty] | 2018-10-02 | 2018-10-09 | 2018-10-11 | 2018-10-25 | 2018-10-31 | 2018-11-07 | 2018-10-31 | 2018-11-07 | 2018-11-09 | 2018-12-11 | 2018-12-15 | 2018-12-22 | 2018-12-27 | 2019-01-05
Actual
| 2 | KARP-CS-3 (ii) | Training and certification of Extension Staff | Planned | 1 | CS | QBS | Post | 320000 |  |  | 320000 | 2017-09-01 | 2017-09-08 | 2017-09-11 | 2017-09-25 | 2017-09-29 | 2017-10-06 | 2017-09-29 | 2017-10-06 | 2017-10-10 | 2017-11-10 | 2017-11-17 | 2017-11-24 | 2017-11-29 | 2017-12-01 | 2021
|  |  |  | Revised | [8 empty] | 2019-02-01 | 2019-02-08 | 2019-02-11 | 2019-02-25 | 2019-03-01 | 2019-03-06 | 2019-03-01 | 2019-03-06 | 2019-03-11 | 2019-04-11 | 2019-04-18 | 2019-04-25 | 2019-04-29 | 2019-05-02
Actual
|  |  | Sub Total - Component 1 | [5 empty] | 560000
|  | Contract # | Description of Assignment | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's review (Prior/Post) | Estimated cost (000 Euro) | Source of finance MDTF | Source of finance IDA | Grant Manual sent to the Bank for NO | Bank's NO to the Grant Manual | Proposal Submission Deadline | Pre selection decision | Final decision date on financing | Contract Signing date | Contract Completion date (refers to the submission deadline of the final progress report and final financial report for the fourth quarter ) | Company name | Remarks
Component 2 - Investments for Sustainable Rural Development
| 1 | KARP-CS-20 | Horticulture Value Chain (Call for Proposal 2018) | Planned | 2 |  | CP | Prior | 1500000 |  |  | 2018-06-28
Revised
Actual
| 1 | KARP-CS-20.1 | Horticulture Value Chain (Call for Proposal 2020) | Planned | 2 |  | CP | Prior | 1500000 |  |  | 2020-01-13
Revised
Actual
|  |  | Sub Total - Component 2 | [5 empty] | 3000000
|  | Contract # | Description of Assignment | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's Review (Prior/ Post) | Initial estimated cost, EUR | Source of finance MDTF | Source of finance IDA | Estimated cost for actual Contract, EUR | TOR and ReOI sent to the bank | Bank's no objection to TOR and ReOI | ReOI Published | Deadline for Submission of ReOI | Shortlist and ReOIs Evaluation Report sent to the Bank | Bank's no objection to the Shortlist and ReOIs Evaluation Report | RFP sent to the Bank | Bank's No objection to RFP | Issue date of the RFP | Proposal Submission Deadline | Evaluation Report sent to the Bank | Bank's NO objection to Evaluation report | Bank's No objection to Contract Award | Contract Signing date | Contract Completion | Consultant's Name | Remarks | Amount reduced from previous estimates |  | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Consultant's name | Comment | Status
Component 3 - Rehabilitation and Modernization of Radoniqi Irrigation Scheme
| 1 | KARP-CS-21 | Investment on Rehabilitation and Modernization of Radoniqi (Multiple Contracts) | Planned | 3 | CS | TBD | Prior | 6000000 |  |  | 6000000 | [24 empty] | Based from the outcome of the feasibility study the activities will be defined
Revised
Actual
| 2 | KARP-CS-21.1 | Monitoring installation equipment for Radoniqi Irrigation scheme | Planned | 3 | CS | TBD | Post | TBD | [27 empty] | Based from the outcome of the feasibility study the activities will be defined. This activity was forseen in KARP CS - 5 (TBD)
Revised
Actual
|  |  | Sub Total - Component 3 | [5 empty] | 6000000
|  | Contract # | Description of Assignment | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's Review (Prior/ Post) | Initial estimated cost, EUR | Source of finance MDTF | Source of finance IDA | Estimated cost for actual Contract, EUR | TOR and ReOI sent to the bank | Bank's no objection to TOR and ReOI | ReOI Published | Deadline for Submission of ReOI | Shortlist and ReOIs Evaluation Report sent to the Bank | Bank's no objection to the Shortlist and ReOIs Evaluation Report | RFP sent to the Bank | Bank's No objection to RFP | Issue date of the RFP | Proposal Submission Deadline | Evaluation Report sent to the Bank | Bank's NO objection to Evaluation report | Bank's No objection to Contract Award | Contract Signing date | Contract Completion | Consultant's Name | Remarks | Amount reduced from previous estimates |  | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Consultant's name | Comment | Status
Component 4 - Project Management, Public Outreach and M&E
| 8 | KARP-CS-8 | Project Manager | Planned | 3 | CS | IC | Post | 99500 | [16 empty] | 2019-04-01 | 2021-06-30
Revised
|  |  |  | Actual |  |  |  |  | 50526.45
| 9 | KARP-CS-9 | Procurement Specialist | Planned | 3 | CS | IC | Post | 70000 | [16 empty] | 2019-04-01 | 2021-06-30
Revised
|  |  |  | Actual |  |  |  |  | 30877.74
| 10 | KARP-CS-10 | Financial Mgt. Specialist | Planned | 3 | CS | IC | Post | 70000 | [16 empty] | 2019-04-01 | 2021-06-30
Revised
|  |  |  | Actual |  |  |  |  | 30877.74
| 11 | KARP-CS-11 | Training Specialist | Planned | 3 | CS | IC | Post | 70000 | [16 empty] | 2019-04-01 | 2021-06-30
Revised
|  |  |  | Actual |  |  |  |  | 37193.85
| 12 | KARP-CS-12 | Monitoring/Evaluation Specialist | Planned | 3 | CS | IC | Post | 70000 | [16 empty] | 2019-04-01 | 2021-06-30
Revised
|  |  |  | Actual |  |  |  |  | 35614.62
| 13 | KARP-CS-13 | Assistant/Interpreter | Planned | 3 | CS | IC | Post | 41000 |  |  |  | 2018-12-03: 2018-03-19; 2018-12-10: 2018-03-26; 2018-12-12: 2018-03-28; 2018-12-27: 2018-04-11; 2018-12-27: 2018-04-13 |  | 2018-04-20 |  | 2018-04-24 | 2018-04-30 | 2021-06-30
|  |  |  | Revised | [8 empty] | 2018-12-03: 2018-05-22; 2018-12-10: 2018-05-29; 2018-12-12: 2018-05-30; 2018-12-27: 2018-06-13; 2018-12-27: 2018-06-18 |  | 2018-06-25 |  | 2018-06-28 | 2018-07-02
Actual
| 14 | KARP-CS-14 | Irrigation Specialist | Planned | 3 | CS | IC | Post | 80000 |  |  |  | 2018-12-03: 2018-03-19; 2018-12-10: 2018-03-26; 2018-12-12: 2018-03-28; 2018-12-27: 2018-04-11; 2018-12-27: 2018-04-13 |  | 2018-04-20 |  | 2018-04-20 | 2018-04-30 | 2021-06-30
|  |  |  | Revised | [8 empty] | 2018-12-03: 2018-05-22; 2018-12-10: 2018-05-29; 2018-12-12: 2018-05-30; 2018-12-27: 2018-06-13; 2018-12-27: 2018-06-18 |  | 2018-06-25 |  | 2018-06-28 | 2018-07-02
Actual
| 15 | KARP-CS-18 | Intermittent Consultants (multiple contracts) | Planned | 3 | CS | IC | Post | 42400
Revised
Actual
| 16 | KARP-CS-AUD | Project Accounts Audits | Planned | 3 | CS | LCS | Post | 30000
Revised
Actual
| 16.1 | KARP-CS-16.1 | Social Surveys | Planned | 3 | CS | CQ | Post | 55000 |  |  | 55000 | 2018-03-05 | 2018-03-12 | 2018-03-14 | 2018-03-28 | 2018-04-03 | 2018-04-10 | 2018-04-03 | 2018-04-10 | 2018-04-12 | 2018-04-26 | 2018-05-03 | 2018-05-10 | 2018-05-11 | 2018-05-15 | 2021-03-01
|  |  |  | Revised | [8 empty] | 2019-03-05 | 2019-03-12 | 2019-03-14 | 2019-03-28 | 2019-04-03 | 2019-04-10 | 2019-04-03 | 2019-04-10 | 2019-04-12 | 2019-04-26 | 2019-05-03 | 2019-05-10 | 2019-05-13 | 2019-05-15
Actual
| 17.2 | KARP-CS-17.2 | Public Awareness Campaign | Planned | 3 | CS | CQ | Post | 50000 |  |  | 50000 | 2017-11-01 | 2017-11-08 | 2017-11-10 | 2017-11-24 | 2017-12-01 | 2017-12-08 | 2017-12-01 | 2017-12-08 | 2017-12-12 | 2017-12-27 | 2018-01-09 | 2018-01-16 | 2018-01-18 | 2018-01-22 | 2021-07-01
|  |  |  | Revised | [8 empty] | 2019-01-08 | 2019-01-14 | 2019-01-15 | 2019-01-29 | 2019-02-01 | 2019-02-05 | 2019-02-01 | 2019-02-05 | 2019-02-06 | 2019-02-20 | 2019-02-27 | 2019-03-04 | 2019-03-08 | 2019-03-20 | 2021-07-01
Actual
|  |  | Sub Total - Component 4 | [5 empty] | 677900
Disbursement Estimates
Procurement category |  | Contract # | Description items |  | Component Nr. | Procurement Type | Procurement method | Bank's Review (Prior/ Post) | Initial estimated cost, EUR | Source of finance MDTF | Source of finance IDA | Actual training value in Euro | Request sent to Bank for no objection | Bank's no objection | RFP/ REI issued | Technical Proposal receipt | Bank's no objection for Technical proposal | Bank's no objection to contract signature | Contract signing date | Training start date | Training Completion date | Training Title | Winning bidder name&Country | Training atendee |  |  |  | Remarks | Amount reduced from previous estimates |  | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Total
(Training ) | 1 | KARP-TR-1 | Training for PA | Planned | 2 |  |  | Prior | 40000 |  |  | 40000
Revised
Actual
| 2 | KARP-TR-2(i) | Training for MA | Planned | 2 |  |  | Prior | 40000 |  |  | 40000
Revised
Actual
| 3 | KARP-TR-4 | Training for KIA STAFF | Planned | 2 |  |  | Prior | 40000 |  |  | 40000 | 2018-12-03: 2019-01-01
Revised
Actual
| 4 | KARP-TR-3(i) | Training for PIU staff | Planned | 3 |  |  | Prior | 40000 |  |  | 40000
Revised
|  |  |  | Actual | [24 empty] | #REF! |  | 500000 | 100000 | 250000 | #REF! | #REF!
|  |  | Total Training | [5 empty] | 160000 | [19 empty] | #REF! |  | 500000 | 100000 | 250000 | #REF! | #REF!
Disbursement Estimates
Provision of Grants
| # | Contract # | Description of goods | Procurement Status | Component Nr. | Procurement Type | Procurement method | Bank's review (Prior/Post) | Estimated cost (000 Euro) | Source of finance MDTF | Source of finance IDA | Grant Manual sent to the Bank for NO | Bank's NO to the Grant Manual | Proposal Submission Deadline | Pre selection decision | Final decision date on financing | Contract Signing date | Contract Completion date (refers to the submission deadline of the final progress report and final financial report for the fourth quarter ) | Company name | Remarks | [7 empty] | Remarks | Amount reduced from previous estimates |  | Disbursed as of 19 Sept. 08 ( to verify) | IV Quarter 2008 | First Half 2009 | Second Half 2009 | Total
| 1 | KARP-GRT-6 | Call for Proposals - 2018 | Planned | 2 |  | CP | Prior | 2300000 |  |  | 2018-03-01
Revised
Actual
| 2 | KARP-GRT-7 | Call for Proposals - 2019 | Planned | 2 |  | CP | Prior | 3000000 |  |  | 2019-03-01
Revised
Actual
| 3 | KARP-GRT-8 | Call for Proposals - 2020 | Planned | 2 |  | CP | Prior | 2500000 |  |  | 2020-03-01
Revised
Actual
| 4 | KARP-GRT-9 | Call for Proposals - 2021 | Planned | 2 |  | CP | Prior | 1000000 |  |  | 2021-03-01
Revised
Actual
|  |  | Sub-total for Rural Grants | [5 empty] | 8800000
19960500